## Migration Checklist
Topic | Source Environment | Item | Description | Severity | Status | Comment
Wave Planning | All environments | Plan migration waves and document with relevant information. | Migration waves should be planned around the grouping of dependent services e.g. application tiers, the criticality of services, the environment (non-production, production), the availability of acceptance testers, the size of replication data, the available network bandwidth, the potential impact on the hosting platform and its supporting services e.g. storage, etc. | Medium | Not verified
Wave Planning | All environments | Evaluate network readiness for planned migration activities. | Total storage directly affects bandwidth requirements during initial replication. However, storage drift continues from the point of replication until release. Calculate the bandwidth needed to reach the anticipated migration velocity. | High | Not verified
Workload Planning | All environments | Intra-Subnet Traffic: Be mindful that security rules in a Network Security Group associated to a subnet can affect connectivity between VMs within the subnet. | This is often the root cause in failover cluster instance migrations to SQL Server on Azure VMs. | High | Not verified
Workload Planning | All environments | Perform pre-migration activities. Document the availability of hybrid benefits for each workload as the information is required for the migration step. | Estimate costs. Perform right-sizing for virtual machines (VMs) and storage. Use Azure Hybrid Benefit. Use Azure Reserved VM Instances, Reserved storage, Reserved backup storage. Compare Azure Savings plans and burstable instances. Estimate cloud spending across subscriptions. | High | Not verified | If hybrid benefit is aplicable.
Workload Planning | All environments | Legacy workloads if any ** | Target legacy workloads to access Microsoft extended security updates. | High | Not verified
Workload Planning | All environments | Confirm Microsoft server software support for Azure VMs. | Microsoft maintains a list of server software that is officially supported on Azure VMs. | High | Not verified
Workload Planning | All environments | Design workload architecture before migration for each workload. The workload architecture will determine placement in the cloud, any prerequisite work that may be required e.g. allowing firewall ports, network communication, deployment of load balancers, placement in availability sets/zones, proximity groups, etc. | In addition to the generic landing zone design and implementation that needs to precede a workload migration, specific architecture planning is also required for each workload. Workloads may have different requirements wrt network, availability services, management and security. | Medium | Not verified
Workload Planning | All environments | Prioritise workloads based on quick wins sand based on Wave Planning | Use the assessment reports to identify low-hanging fruit, including servers and databases that are fully ready, and require minimal effort to migrate to Azure. | Low | Not verified
Workload Planning | All environments | For each workload, choose and document the desired disk encryption option. | Encryption-at-rest with platform-managed key Encryption-at-rest with customer-managed key Double encryption with platform-managed and customer-managed keys | Medium | Not verified
Workload Planning | All environments | For each workload, choose an availability option and document it in the workload plan. | Availability Set Availability Zone No infrastructure redundancy required option | High | Not verified
Workload Planning | All environments | Do not migrate domain controllers unless migrating into an isolated environment in Azure requiring its own domain controllers (or testing applications in a sandbox environment). | It is recommended that additional domain controllers be built and replicated to using AD DS services rather than migrated. | High | Not verified | (Optional to Gassco) KIS: I recommend going with Domain Services only if strategy/workloads deem it necessary.
Workload Planning | All environments | Verify that the desired VM Sku is available in the target region prior to migration. Also confirm that Azure Policy is not blocking the VM Sku, and that the target subscription has sufficient available quota. |  | High | Not verified
Workload Planning | All environments | 3'rd part vendors access | When relevant Make shure 3'rd partys have access
Workload Planning | All environments | Remove on-premises operational software and configuration (agents, Group Policy, scheduled scripts) | On-premise operational software and configuration may interfere and spend unnecessary resources when moved to cloud environment | Medium | Not verified
Workload Planning | All environments | Verify that the VM has appropriate configuration for connectivity to external services | Ensure proxy settings/routing is set correctly to ensure outbound connectivity | High | Not verified | KIS: Did not find a line regarding outbound/proxy settings, thought that might be added considering our current reliance on it.
Workload Planning | All environments | Monitor resource consumption including disk capacity and utilization on replicating machines, appliances and host systems. | Configure alerting. | Medium | Not verified
Landing Zone | All environments | Ensure there is a suitable Landing Zone available to host the migrated workloads. | The FTA landing zone checklist can be used to review a landing zone design. | High | Not verified
Test Migration | All environments | Plan to perform workload UAT during a test migration for each workload. | Use a non-production vnet and subnet to host and validate the VMs as part of the test migration. | High | Not verified
Workload Preparation | All environments | Check Windows Application and System event logs for any errors. |  | Medium | Not verified
Workload Preparation | All environments | Create a detailed migration rollback plan. | Prepare a rollback plan for the workload in case of workload issues during or after migration. Note: Once you've performed a final migration to Azure and the on-premises source machine was shut down, you can't perform a rollback from Azure to your on-premises environment using Azure Migrate. Any rollback plan after final migration would need to be based on features external to Azure Migrate e.g. backups and restore. | High | Not verified
Workload Preparation | All environments | Test migration plan and record timings. |  | High | Not verified
Workload Preparation | All environments | Test rollback plan and record timings. |  | High | Not verified
Workload Preparation | SQL Server | If existing databases have Transparent Data Encryption (TDE) enabled, ensure that the protector will be migrated and protected within Azure. | When migrating to SQL Server: Certain steps to follow | High | Not verified
Workload Preparation | SQL Server | Check SQL Server Error Log for any ongoing errors. |  | Medium | Not verified
Workload Preparation | SQL Server | Check SQL Server Error Log for any errors at last startup. |  | Medium | Not verified
Workload Preparation | SQL Server | Check SQL Server Agent for any failing jobs. |  | Medium | Not verified
Workload Preparation | SQL Server | Tidy up SQL Server Agent jobs that are no required (and therefore don't need to be migrated). |  | Medium | Not verified
Network | SQL Server | if using SQL Clusters and the migration is to new VMs and Windows Firewall is in use, ensure Windows Firewall rules are open to allow failover clustering to communicate between the VMs. |  | High | Not verified
Network | SQL Server | if using SQL Clusters, ensure Network Security Groups have allow rules for failover cluster communication ports. |  | High | Not verified
Replication | VMware | Review common replication bottlenecks through testing and validation. | The replication speed of initial migration in a Migrate Appliance infrastructure, has many factors to consider. Usually the appliance is in vCenter as a VM and its disks reside in a data store. Possible bottlenecks: 1. Replication bandwidth between appliance and Azure / storage account. Monitor connection e.g. ExpressRoute. Test speed between appliance and cache storage account using azcopy bench. 2. Monitor appliance performance for CPU/RAM/Network (inbound and outbound) as well as disk IOPS. 3. Replication bandwidth between the ESXi host and appliance. 4. Source VM disk IOPS. 5. Combination of the above. Trigger an initial replication to monitor and benchmark all of the above. | High | Not verified
Replication | VMware Agentless | Decide if blackout windows are required to define intervals during which replication is not allowed. | Customers may prefer to schedule replication during non-business hours or off-peak periods. Replication issues during periods when there are resource contention is a frequent root cause for support incidents. | Low | Not verified
Licensing | All environments | Verify and troubleshoot any Windows activation issues on the Azure VM. |  | High | Not verified
Linux | VMware Agent-based | Install the Azure VM agent on Linux VMs after migration. | The Azure VM agent manages VM interaction with the Azure Fabric Controller. It's required for some Azure services, such as Azure Backup, Site Recovery, and Azure Security. When migrating VMware VMs with agent-based migration, the Mobility Service installer installs Azure VM agent on Windows machines. On Linux VMs, it is recommend to install the agent after migration. | Medium | Not verified
Replication | All environments | Factor stop replication duration into change management and cost considerations. | As a best practice, always complete the migration after a VM has migrated successfully to Azure to ensure that extra charges for storage transactions on the intermediate managed disks (seed disks) are not incurred. Be mindful that in some cases, stop replication takes time. It is because whenever replication is stopped, the ongoing replication cycle is completed (only when the VM is in delta sync) before deleting the artifacts. The time taken to stop replication has a high volume of support incidents. | High | Not verified
Target: Azure SQL Database (Database Migration Service) | SQL Server | Consider using the Azure SQL Migration extension for Azure Data Studio with DMS for migrating to Azure SQL Database as the target from SQL Server. | DMS supports Schema and offline data migration scenarios. Consider Cloudamize, Attunity and Striim for online migration scenarios. | Medium | Not verified
Target: Azure SQL Managed Instance (Database Migration Service) | SQL Server | Consider using the Azure SQL Migration extension for Azure Data Studio with DMS for migrating to Azure SQL Managed Instance as the target from SQL Server. | DMS supports Schema, offline and online data migration scenarios. | Medium | Not verified
Target: SQL Server on Azure VMs with/without SQL Server Always On Availability Groups (Database Migration Service) | SQL Server | Consider using the Azure SQL Migration extension for Azure Data Studio with DMS for migrating to SQL Server on Azure VMs with or without SQL Server Always On Availability Groups as the target from SQL Server. | DMS supports Schema and offline data migration scenarios. Consider Azure SQL Migration extension, Cloudamize, Attunity and Striim for online migration scenarios. | Medium | Not verified
Tooling | All environments | Plan for existing backups to be migrated. | Ensure existing and historical on premises backups can be restored and retained in line with legal requirements. Consider using reserved backup storage for long term backup retention. Decide if a 3rd party backup tool will be used, or if backups will be migrated to Azure Backup. |  | Not verified | Not verified
Tooling | All environments | Plan for password and key storage post migration | Will the customer use a third party solution or a key vault. Who needs access post migration. Ensure access to the current password and key management store is available to the migration team. |  | Not verified | Not verified
Tooling | All environments | Plan for SME/app owner access to new monitoring, backup, budget, observability portals. | So they can manage the applications and have visibility of their health. |  | Not verified | Not verified
Tooling | All environments | Confirm logins for SSL Cert , domain name management and external DNS portals are available. | Ensure someone in the business is able to log in and manage these resources prior to migration. Document any new SSL certs that will need to be purchased. |  | Not verified | Not verified
Tooling | All environments | Validate Application Licencing Model. | Confirm how the application license will be activated post migration. Note that some apps may rely on a dongle, static MAC or IP address. |  | Not verified | Not verified
Tooling | All environments | Operations of Cloud enviroment | Make sure there are responsible parties operating cloud enviroment with all neseccarry tools for health and security reporting. | High | Not verified
Tooling | All environments | Create and maintain Documentation | Document whitch and how tools are used, and whitch routines are in place for operating cloud enviroment. |  | Not verified
Tooling | All environments |  |  |  | Not verified
Tooling | All environments |  |  |  | Not verified

## Migration Cut Over
Cutover Plan |  |  |  |  | Planned |  |  | Actual
Milestone | Task | Responsible | Owner | Status | Start Date | End Date | Duration | Start Date | End Date | Duration | Remarks
MS 1 (T-2 Week)Pre-Migration Checklist | [11 empty] | Completed
MS1 | Inventory Freeze for the Servers in scope for Migration | GASSCO Infra PMO |  | Not Started | [7 empty] | Delayed
MS1 | Migration SMEs (Cloud/Security/Database/Application/Testing) are aligned for testing and migration | GASSCO | GASSCO PMO | Not Started | [7 empty] | Not Started
MS1 | Migration Contacts are updated in Plan | GASSCO |  | Not Started | [7 empty] | In Progress
MS1 | Confirm migration SMEs have required access on target & source servers (including local admin access) | GASSCO/App Owner | [9 empty] | Failed
MS1 | Operations Team (Server Group) is aligned for post migration handover | GASSCO | [9 empty] | Not Required
MS1 | Migration Communication Recepient List | GASSCO/Client
MS1 | Cutover Plan Review along with Client | GASSCO
MS1 | Sign-off Cutover Plan from client | App Owner / Client
MS1 | RFC Submission along with Cutover Plan. | GASSCO
MS1 | Migration Pre-requisites : Firewall Rules to be open at Firewall, Network changes, Backups in On-Premises | GASSCO
MS-2 (T-1 Week)Pre Cutover Activites
MS2 | Request for Change approved
MS2 | Replicate servers using Azure Migrate/ASR (Optional) |  |  | Not Required
MS2 | Reserve IP Addresses
MS2 | Firewall rules implementation for on premise (with new IP address)
MS2 | AV policies and exclusions to be provided
MS2 | Firewall rules implementation for Azure Firewall (Rules will remain in Disable State)
MS2 | Confirmation needed for any application changes pointing to mail relay server as per cutover document
MS-3 (T-1 Day) Pre-Cutover Infra testing / GO / No-GO call
MS3 | Verify the Azure Firewall Health
MS3 | Verify AD/DNS Servers Connectivity with in Azure Cloud | Server Group | Karl Ivar | Completed
MS3 | Verify if Firewall Rules are in Place at On-premises Firewall (As Applicable)
MS3 | Splunk Monitoring Tools Infrastructure Connectivity in place
MS3 | Inform Resource to suspend the monitoring of the servers.
MS3 | Backup Infrastructure Readiness
MS3 | Express Route Network Connectivity Validation
MS3 | Go/NO Go Call Meeting (Internal)
MS3 | Go/NO Go Call Meeting (External)
MS-4 (T-Cutover) Application Shutdown
MS4 | Validation of system state backup (App)
MS4 | Validation of Database Server Backup
MS4 | Graceful Shutdown of all Database Services (If Applicable).
MS4 | Graceful Shutdown of all Application Services
MS4 | Shutdown the server (application and database)
MS4 | Change IP , update DNS for Web URLs (If Applicable).
MS4 | Send a communication to MS1 Communication Plan reciepient list
MS-5 (T-Cutover) Migration Commencement
MS5 | Start the Test failover
MS5 | Verify the Test failover is successful (Infra)
MS5 | Start the Actual failover
MS5 | Verify the Actual Failover
MS5 | Install the AV, Backup, Monitoring, Ivanti on servers
MS5 | View Database logs in SQL Server for any Errors
MS5 | Onboard server in backup
MS5 | Onboard Server in Monitoring
MS5 | Firewall rules implementation for Azure Firewall.
MS5 | Change the New IP with Existing Host Name in Domain
MS-6 (T-Cutover) Infrastructure Testing after cutover
MS6 | Test connectivity to all application Workloads
MS6 | Test machine health from Azure Portal
MS6 | Verify all tool agents have been uninstalled (Which are not required).
MS6 | Verify all GASSCO Tool agents have been installed (as per new Target state).
MS6 | Test the DNS changes
MS6 | Verify the Name of the attached Disks Drives
MS6 | Verify the logs in Firewall
MS6 | Server is onboarded in the Ivanti Console
MS-7 (T-Cutover) Application Start-up and Testing
MS7 | Pre-checks before App testing initiation (Infra and App team sync up to do the basic validation as per the App test plan)
MS7 | Application Configuration
MS7 | Application Testing
MS7 | Go/NO Go Call Meeting - Or Rollback Decision
MS7 | Go Live Initiated and Signoff Migration as Successful
MS7 | If Unsuccessful, Initiate Rollback (Bring Server back online in Source DC)
MS-8 (T-Cutover) Roll back plan
MS8 | Switch off the servers in Azure.
MS8 | Switch ON Servers in Datacenter
MS8 | Enable monitoring (as per the policy)
MS8 | Enable backup (as per the policy)
MS8 | Full restore (--> Application+tooling) - If required (VM)
MS8 | Update configurations on infra servers
MS8 | Infra Readiness Validation
MS-9 (T-Cutover) Roll back Testing (This need to be done by Ops Team for Infra & Application Owner)
MS9 | Application Testing
MS9 | Verify the Firewall Probe Nodes health
MS9 | Verify the logs on Firewall
MS9 | Resume SLAs
MS9 | Move to production
MS9 | Cisco Firewall - Disable the access rules for Azure.
MS9 | Roll back the DNS Record to previous IP (External IP)
MS-10 Ops Team Handover (Post successful rollback completion)
MS10 | Initiate the Ops Team handover process for the migrated servers
MS10 | Handover Asset list and checklist checklists with notes, CMDB to be updated by Ops Team
MS10 | Send a communication to milestone-8 recepeients about Ops Team handover (INFRA-Comms update)

## Risk Registration
Application will not be available during cutover window
Downtime will increase in case of rollback (Rollback plan given)
Risk | Severity | Impact | Mitigation
IP Address will be changed of server Post Migration to Public Cloud. | Medium | Incase application is Bind or any integrations Happened with Server's IP Address then Application or Integrated connections may break | Application Owner need to change the Application code to DNS level rather than Dependency on IP Address.
Implementation of NSG will create microsegmentation which is not in the envrionment today | Critical | If there is any port to be opened which is not known to us during pre-cutover then there would be a delay (troubleshooting period- couple of hrs) in application testing and subsequent go-live as well. | Application team to confirm the NSG/Firewall rules which needs to be open between servers. DMZ Prodcution servers will be blocked
Firewall Rules Details are still pending for every application | High | If there is any port to be opened which is not known to us during pre-cutover then there would be a delay (troubleshooting period- couple of hrs) in application testing and subsequent go-live as well. | Application team to confirm the Firewall rules which needs to be open between servers.
IP Address an Mac Address will be changed of server Post Migration to Public Cloud. | Medium | Incase application is Bind or any integrations Happened with Server's IP Address then Application or Integrated connections may break | Application Owner need to change the Application code to DNS level rather than Dependency on IP Address.
Firewall Rules Details Verification for every application. | High | If there is any port to be opened which is not known to us during pre-cutover then there would be a delay (troubleshooting period- couple of hrs) in application testing and subsequent go-live as well. | List down all Firewall Rule details and validated by Application team.

## Current Details
DMZ | Disks | File Share Dependency | DFS Server name (File Server) | File Share Path Mapped with Application | Public DNS | Public IP | Horizon | Current SLA | Environment | DR | Firewall | Web URL | SSL Requriement | SSL Certificate | SSL Offload at Server or LB

## Target App Mapping
Server Name | Application Names | Dependent Application | Dependent Application Server Names | Port information | Additional Dependency | Pre-migration communications date
,

## Target Details
Server Name | Primary Server IP Address | Secondary IP (Dedicated for Backup Traffic) | OS | MSSQL Version | DNS Name | SMTP | Internet Requirement | Antivirus Exclusions | Managed Disk Encryption - keys Managed by Microsoft (Auto Encryption) | Standalone or Cluster | DMZ | IOPS Disk | Storage Type (Managed Disk) | File Share Dependency | DFS Server name (File Server) | File Share Path Mapped with Application | Azure Subscription | Resoruce Group | Virtual Network | Subnet | Availability Set / Availbility Zone (If applicable) | Current SLA | Environment | Target Instance Size | DR | Backup

## Contact Details
Name | Role | Phone | Org | Location | Email
Please add the other Infra SME/Architect and Business Support Team details
Please add the Application Team details